LARF

LLM-Based Autonomous Remediation Framework

Self-Correcting Agentic Data Pipelines for Healthcare

| Bhuvanesh D 22PD07 | V S Ritanya 22PD38 |
| --- | --- |

Project Planning & Implementation Guide

Version 1.0  ·  2026

# 1. Project Overview

This document is the single source of truth for building LARF — a closed-loop, AI-powered self-healing data pipeline. It covers everything your two-person team needs: concept, architecture, sprint plan, task assignments, GitHub repo structure, and coding guidance.

What problem are we solving?

Healthcare data pipelines (EHR → Kafka → Databricks/Snowflake → Clinical Dashboards) break constantly. When they break, a human engineer has to:

- Receive an alert (often delayed)

- Read logs and metrics manually

- Diagnose the root cause

- Write and execute a fix

- Verify recovery

Average time: 47 minutes. In healthcare, 47 minutes of stale data is a patient risk and a HIPAA compliance event.

What is LARF?

LARF replaces that manual loop with an autonomous AI agent that observes, diagnoses, and fixes pipeline failures in under 4 minutes — without human intervention.

It is built on the OODA loop: Observe → Orient → Decide → Act, with a memory layer (ChromaDB) that makes the system smarter after every incident.

Key results (from the reference paper)

| Metric | Manual | LARF | Improvement |
| --- | --- | --- | --- |
| Mean Time to Recovery | 47.2 min | 3.7 min | ~92% reduction |
| Diagnosis Accuracy | 100%* | 94.2% | Near-human |
| Successful Remediation | 100%* | 92.5% | Production-ready |
| False Positives | 0 | 3 / 120 tests | Acceptable |

* Human baseline assumes expert engineer with full context.

# 2. System Architecture

The system has two layers: the data pipeline (the infrastructure being protected) and the LARF cognitive layer (the AI protection system).

## 2.1  Data Pipeline Layer

This is the infrastructure you are protecting. You will simulate it since a real hospital Kafka/Snowflake setup is not available.

| Component | Description |
| --- | --- |
| EHR / IoT / Genomics | Data sources that produce patient events (heart rate, blood pressure, oxygen saturation, genomic reads) |
| Apache Kafka | High-throughput event streaming bus. Topics: ehr-stream, iot-vitals, genomic-data |
| Databricks / Snowflake | Cloud data warehouse for structured storage and analytics queries |
| Clinical Dashboards | Downstream consumers: real-time vitals monitors, predictive analytics |

## 2.2  LARF Cognitive Layer (the 4 phases)

Phase 1 — Observe (Infrastructure Telemetry)

Attaches monitoring probes to Kafka and Databricks. Two detection algorithms run continuously:

- Z-Score Anomaly Detection: Flags any single metric (consumer lag, latency, CPU) that exceeds 3 standard deviations from its rolling mean. Fast, interpretable.

- Isolation Forest: Detects multivariate anomalies — combinations of metrics that look suspicious together even if no single one is extreme. Catches compound failures.

Phase 2 — Orient (Data Integrity Mining)

Catches 'silent failures' where data flows but content is wrong:

- Kolmogorov-Smirnov (KS) Test: Compares the statistical distribution of incoming streaming data against a stored 'Gold' baseline. If p < 0.05, the data has drifted significantly — e.g., heart rates suddenly clustering at 200 BPM.

- Schema Entropy Mapping: Calculates the structural distance between the incoming JSON payload and the expected Delta Lake schema. A new field, renamed field, or type change shows up as high entropy distance.

Phase 3 — Decide (LLM Agentic Reasoning)

When a fault is detected, Phases 1 and 2 package the evidence into a Crisis Packet and hand it to the LLM agent:

- Chain-of-Thought (CoT) Prompting: Forces the LLM to reason step-by-step before committing to a diagnosis. Reduces hallucinations because every conclusion must follow from evidence.

- ReAct (Reason + Act) Algorithm: The agent iteratively thinks, queries your metadata catalog or system logs for more information, thinks again, and only then proposes a fix. It never guesses blindly.

Phase 4 — Act (Autonomous Remediation)

Executes the fix safely and verifies it worked:

- Vector Similarity Search (ChromaDB): Looks up the historical incident store for similar past failures and their proven fixes. The agent applies a known-good pattern rather than improvising.

- Deterministic SQL Sanitization: A whitelist guardrail that blocks any destructive SQL command (DROP, TRUNCATE, DELETE without WHERE) before execution. Enterprise safety baseline.

- Post-Fix Validation: After applying a fix, re-runs the Phase 1 and 2 statistical tests to confirm the pipeline has returned to steady state. The loop does not close until this passes.

# 3. GitHub Repository Structure

Organise your repository exactly as shown below. Each folder maps to one phase of the OODA loop. This separation makes code reviews, testing, and debugging much simpler.

larf-pipeline/

│

├── README.md                     # Project overview + quickstart

├── requirements.txt              # All Python dependencies pinned

├── .env.example                  # Template for API keys (never commit .env)

├── .gitignore

├── docker-compose.yml            # Local Kafka + Zookeeper + Schema Registry

│

├── simulator/                    # Sprint 1 — Synthetic data + fault injection

│   ├── __init__.py

│   ├── patient_generator.py      # Produces realistic EHR/IoT events

│   ├── kafka_producer.py         # Streams events to Kafka topics

│   ├── fault_injector.py         # Triggers the 5 fault categories on demand

│   ├── gold_baseline.py          # Captures and stores 'normal' distributions

│   └── schemas/

│       ├── ehr_v1.json           # Original EHR JSON schema

│       └── ehr_v2.json           # Evolved schema (used in schema fault tests)

│

├── detectors/                    # Sprint 2 — Statistical anomaly detection

│   ├── __init__.py

│   ├── zscore_detector.py        # Z-Score on single metrics

│   ├── isolation_forest.py       # Multivariate anomaly detection

│   ├── ks_test.py                # KS drift test against gold baseline

│   ├── schema_entropy.py         # Structural distance between schemas

│   └── telemetry_collector.py    # Polls Kafka / Databricks metrics

│

├── agent/                        # Sprint 3 — LLM orchestration

│   ├── __init__.py

│   ├── orchestrator.py           # Main OODA loop coordinator

│   ├── crisis_packet.py          # Builds structured fault evidence dict

│   ├── prompts.py                # All system + CoT prompt templates

│   ├── react_agent.py            # ReAct reasoning loop using LangChain

│   └── tools/

│       ├── schema_tool.py        # Schema registry read/update/rollback

│       ├── sql_tool.py           # Execute whitelisted SQL repairs

│       ├── infra_tool.py         # Scale connectors / warehouses

│       └── security_tool.py      # Quarantine topics / suspend sessions

│

├── remediation/                  # Sprint 4 — Execution + memory

│   ├── __init__.py

│   ├── action_executor.py        # Runs tool commands safely

│   ├── sql_sanitizer.py          # Whitelist guardrail for SQL

│   ├── memory_store.py           # ChromaDB incident vector store

│   ├── validator.py              # Post-fix statistical verification

│   └── incident_logger.py        # Immutable audit trail writer

│

├── tests/

│   ├── test_detectors.py

│   ├── test_agent.py

│   ├── test_remediation.py

│   └── test_end_to_end.py        # Full fault injection → fix scenarios

│

├── notebooks/                    # Jupyter notebooks for analysis / demos

│   ├── 01_baseline_analysis.ipynb

│   ├── 02_detector_tuning.ipynb

│   └── 03_results_dashboard.ipynb

│

└── docs/

├── architecture.md

└── fault_taxonomy.md

## 3.1  Key files explained

| File | Why it exists |
| --- | --- |
| docker-compose.yml | Gives you a local Kafka cluster without any cloud account. Run: docker-compose up -d |
| fault_injector.py | The most important file in Sprint 1. You control exactly what breaks and when — essential for repeatable testing. |
| gold_baseline.py | Captures 30 minutes of normal data. The KS-Test in Sprint 2 compares everything against this. |
| crisis_packet.py | The bridge between detection and the LLM. A well-structured packet = accurate diagnosis. |
| prompts.py | Central repository of all LLM prompts. Keep them here so you can iterate without touching logic code. |
| sql_sanitizer.py | Safety-critical. Every SQL string must pass through this before execution. Blocks DROP, TRUNCATE, DELETE without WHERE. |
| incident_logger.py | Writes every detection + diagnosis + action to an append-only log. Required for HIPAA audit trails. |

# 4. Sprint Plan  (4 Sprints × 2 Weeks)

The project is divided into four two-week sprints. Each sprint builds on the previous one. Do not start Sprint 2 until Sprint 1 tests pass.

Sprint 1 — Simulate the Pipeline (Weeks 1–2)

Goal: Create a realistic, controllable test environment. Every subsequent sprint depends on this.

| Bhuvanesh (22PD07) | Ritanya (22PD38) |
| --- | --- |
| Set up Docker Compose with Kafka + Zookeeper + Schema Registry | Write patient_generator.py: realistic EHR events (HR, BP, SpO2, temperature) |
| Write kafka_producer.py: stream events to 3 Kafka topics | Write fault_injector.py: implement all 5 fault categories |
| Set up Snowflake free trial account + create target tables | Write gold_baseline.py: run 30 min clean stream, save stats to JSON |
| Configure Kafka Connect Snowflake Sink connector | Write ehr_v1.json and ehr_v2.json schemas (v2 adds a nullable field) |
| Create GitHub repo, branch strategy, push initial structure | Write test_simulator.py: verify each fault type triggers correctly |

Sprint 1 Done Criteria: You can run fault_injector.py --fault schema and see a schema mismatch error appear in Kafka Connect logs. All 5 fault types trigger reliably.

Sprint 2 — Build the Detectors (Weeks 3–4)

Goal: Automatically detect every fault type before the LLM agent exists. This sprint gives LARF its 'eyes'.

| Bhuvanesh (22PD07) | Ritanya (22PD38) |
| --- | --- |
| Write telemetry_collector.py: poll Kafka consumer lag, broker metrics every 5s | Write zscore_detector.py: rolling mean + std, flag if ¦z¦ > 3.0 |
| Write isolation_forest.py: sklearn IsolationForest on [lag, latency, cpu, mem] | Write ks_test.py: load gold baseline JSON, run ks_2samp, flag if p < 0.05 |
| Write schema_entropy.py: compute JSON schema diff distance metric | Tune thresholds: inject each fault, measure false positive rate |
| Build telemetry pipeline: collector → detectors → alert dict output | Write test_detectors.py: unit tests for each detector with synthetic data |
| Benchmark: run all 5 fault types, record detection accuracy | Document which detector catches which fault type in fault_taxonomy.md |

Sprint 2 Done Criteria: Running the full detector pipeline against each of the 5 injected faults achieves > 90% detection accuracy with < 5% false positive rate.

Sprint 3 — Build the LLM Agent (Weeks 5–6)

Goal: Give the system a reasoning brain. The agent must produce a correct diagnosis + action plan from a Crisis Packet.

| Bhuvanesh (22PD07) | Ritanya (22PD38) |
| --- | --- |
| Write crisis_packet.py: assemble detector outputs into a structured dict with fault_signals, timestamps, affected_components | Write prompts.py: system prompt with pipeline topology + schema + normal baselines |
| Write schema_tool.py and infra_tool.py as LangChain Tool wrappers | Write sql_tool.py and security_tool.py as LangChain Tool wrappers |
| Write react_agent.py: LangChain ReAct agent with all 4 tools + ChromaDB retriever | Write CoT prompt template: force agent to list evidence → hypothesis → confidence → action |
| Write orchestrator.py: connect detectors → crisis_packet → agent → action_executor | Test each tool in isolation: verify schema_tool updates registry correctly |
| End-to-end test for Schema Fault: inject → detect → diagnose → fix | End-to-end test for Data Quality Fault: inject → detect → diagnose → quarantine |

Sprint 3 Done Criteria: The agent correctly diagnoses and executes the right fix for at least 3 of the 5 fault types without human intervention.

Sprint 4 — Harden & Evaluate (Weeks 7–8)

Goal: Add the memory layer, close the verification loop, run the full 120-test evaluation, and prepare the demo.

| Bhuvanesh (22PD07) | Ritanya (22PD38) |
| --- | --- |
| Write memory_store.py: ChromaDB store, embed incidents as vectors, retrieve top-3 similar on new fault | Write sql_sanitizer.py: regex whitelist check, unit-tested against all destructive commands |
| Write validator.py: re-run KS-test + z-score after fix, return STEADY_STATE or STILL_ANOMALOUS | Write incident_logger.py: append-only JSON-lines log with timestamp, fault, diagnosis, action, result |
| Run full 120-test evaluation: 30 × 5 fault categories, record MTTR and success rate | Write test_end_to_end.py: automated evaluation harness, generates results CSV |
| Build results dashboard in 03_results_dashboard.ipynb: MTTR comparison chart, confusion matrix | Prepare demo script: 5-minute live walkthrough injecting a schema fault and watching LARF fix it |
| Write final README.md with architecture diagram, setup instructions, results summary | Final code review: check all tests pass, remove hardcoded secrets, tag v1.0 release |

Sprint 4 Done Criteria: 120-test evaluation complete with > 90% success rate and documented MTTR. README allows a new person to set up and run the project in under 30 minutes.

# 5. The 5 Fault Categories

These are the exact fault types you must implement in fault_injector.py. Each row tells you what to inject, which detector should catch it, and what the agent should do.

| Fault Type | What to inject | Detector | Expected fix |
| --- | --- | --- | --- |
| Schema Fault | Add a new required field to ehr_v2.json. Send v2 events while Snowflake expects v1. | schema_entropy.py (high distance score) | Update Avro schema in registry to v2. Restart Kafka Connect task. |
| Data Quality Fault | Set heart_rate = 350 BPM for 20% of ICU events. Values exceed physiological range. | ks_test.py (distribution shift detected) | Route anomalous records to quarantine Kafka topic. Alert data steward. |
| Performance Fault | Throttle Snowflake virtual warehouse to X-Small while running heavy aggregation. | zscore_detector.py (query duration z-score > 3) | Scale warehouse to LARGE. Monitor for 5 min. Scale back down. |
| Security Fault | Simulate 50 rapid queries from the same user session in 10 seconds (brute-force pattern). | isolation_forest.py (query rate + session age anomaly) | Suspend user session. Write security event to incident log. Notify. |
| Pipeline Stall Fault | Kill the Kafka Connect task process via SIGKILL to simulate transient network loss. | zscore_detector.py (consumer lag spike) | Call Kafka Connect REST API to restart the specific failed task. |

# 6. Technical Stack & Setup

## 6.1  Python Dependencies  (requirements.txt)

# Data pipeline simulation

confluent-kafka==2.3.0

faker==24.0.0

snowflake-connector-python==3.7.0

# Statistical detectors

scipy==1.12.0

scikit-learn==1.4.0

numpy==1.26.4

pandas==2.2.0

great-expectations==0.18.0

# LLM agent

langchain==0.1.12

langchain-openai==0.0.8

openai==1.12.0

pydantic==2.6.0

# Memory / vector store

chromadb==0.4.24

sentence-transformers==2.5.0

# SQL safety

sqlglot==23.0.0

# Testing

pytest==8.0.0

pytest-cov==4.1.0

## 6.2  Environment Variables  (.env.example)

# OpenAI

OPENAI_API_KEY=your-key-here

OPENAI_MODEL=gpt-4-turbo-preview

# Kafka (local Docker)

KAFKA_BOOTSTRAP_SERVERS=localhost:9092

SCHEMA_REGISTRY_URL=http://localhost:8081

# Snowflake (free trial)

SNOWFLAKE_ACCOUNT=your-account

SNOWFLAKE_USER=your-user

SNOWFLAKE_PASSWORD=your-password

SNOWFLAKE_DATABASE=HEALTHCARE_DB

SNOWFLAKE_WAREHOUSE=ANALYTICS_WH

# LARF settings

DETECTION_INTERVAL_SECONDS=5

ZSCORE_THRESHOLD=3.0

KS_PVALUE_THRESHOLD=0.05

SCHEMA_ENTROPY_THRESHOLD=0.3

## 6.3  Git Workflow

Follow this branching strategy:

| Branch | Purpose |
| --- | --- |
| main | Production-ready code only. Protected branch — no direct pushes. |
| develop | Integration branch. Merge feature branches here first. |
| feature/sprint1-simulator | Bhuvanesh Sprint 1 work |
| feature/sprint1-faults | Ritanya Sprint 1 work |
| feature/sprint2-detectors | Sprint 2 detection code |
| feature/sprint3-agent | Sprint 3 LLM agent code |
| feature/sprint4-memory | Sprint 4 ChromaDB + validation |

Rule: Always open a Pull Request to merge into develop. The other person reviews before merging. This prevents broken code from blocking your partner.

# 7. Implementation Guidance  (Where to Start)

## 7.1  Start here on Day 1

- Clone the repo and run Docker: docker-compose up -d starts local Kafka. Verify with kafkacat -L -b localhost:9092

- Write patient_generator.py first: Generate a dict like { patient_id, heart_rate, bp_systolic, bp_diastolic, spo2, temperature, timestamp } using Faker + random within physiological ranges.

- Stream 100 events successfully: kafka_producer.py should push events to the ehr-stream topic. Verify in Kafka UI (port 8080 in docker-compose).

- Capture your gold baseline: Run gold_baseline.py for 30 minutes of normal data. Save the per-column mean, std, min, max, and full distribution arrays to baselines/ehr_baseline.json.

- Inject your first fault: fault_injector.py --fault schema should break the pipeline. Verify the error appears in Kafka Connect logs before moving to Sprint 2.

## 7.2  Most critical code snippet — Crisis Packet structure

The crisis packet is the bridge between your detectors and the LLM. Structure it exactly like this:

# crisis_packet.py

def build_crisis_packet(detector_outputs: dict) -> dict:

"""

Packages all detector signals into a structured dict

that the LLM system prompt can reason over.

"""

return {

"timestamp": datetime.utcnow().isoformat(),

"affected_topics": detector_outputs.get("topics", []),

"fault_signals": {

"zscore_anomalies": detector_outputs.get("zscore", {}),

"isolation_forest_score": detector_outputs.get("if_score", None),

"ks_test_pvalue": detector_outputs.get("ks_pvalue", None),

"schema_entropy_distance": detector_outputs.get("entropy", None),

"consumer_lag_delta": detector_outputs.get("lag_delta", None),

},

"recent_changes": [],   # Pull from git log or change events

"pipeline_topology": load_topology_from_config(),

"normal_baselines": load_baselines(),

}

## 7.3  The CoT System Prompt structure

Your system prompt in prompts.py should include all of these sections in order:

- Role: You are an expert data reliability engineer specialising in healthcare Kafka-Snowflake pipelines.

- Pipeline context: Paste in the topology, normal baselines, schema definitions.

- Fault taxonomy: List all 5 fault types with their typical symptoms. The LLM uses this as a reference.

- Reasoning instruction: Before proposing a fix, you must: (1) List all observed anomaly signals. (2) Rank the top 3 hypotheses with confidence %. (3) State which signal confirms your top hypothesis. (4) Only then call a tool.

- Safety rules: Never execute DROP, TRUNCATE, or DELETE without WHERE. Always call validator after any fix.

## 7.4  SQL Sanitizer — non-negotiable safety layer

# sql_sanitizer.py

import re

BLOCKED_PATTERNS = [

r"\bDROP\b",

r"\bTRUNCATE\b",

r"\bDELETE\b(?!.*\bWHERE\b)",   # DELETE without WHERE

r"\bALTER\s+USER\b",

r"\bGRANT\b",

r"\bREVOKE\b",

]

def sanitize(sql: str) -> str:

"""Raises ValueError if SQL contains blocked patterns."""

upper = sql.upper()

for pattern in BLOCKED_PATTERNS:

if re.search(pattern, upper):

raise ValueError(f'Blocked SQL pattern detected: {pattern}')

return sql

# 8. Evaluation Plan

Your evaluation replicates the methodology from the reference paper. Run 120 discrete fault injection tests (24 per fault type), measure the following metrics, and compare against the manual baseline.

## 8.1  Metrics to measure

| Metric | How to measure | Target | Notes |
| --- | --- | --- | --- |
| MTTR | time_fixed - time_fault_injected in seconds | < 4 min avg | Log both timestamps in incident_logger.py |
| Diagnosis Accuracy | Correct root cause / total faults diagnosed | > 90% | Compare LLM diagnosis to ground truth from fault_injector |
| Remediation Success | Pipeline returned to steady state / total attempts | > 88% | Validator.py must return STEADY_STATE |
| False Positive Rate | Alerts with no real fault / total alerts | < 8% | Run detectors on 30 min clean data |
| Memory Improvement | Success rate in tests 61-120 vs tests 1-60 | Positive trend | ChromaDB should improve accuracy over time |

## 8.2  Test harness structure (test_end_to_end.py)

# Run this to generate your results CSV

for fault_type in ['schema','data_quality','performance','security','stall']:

for i in range(24):

t0 = time.time()

fault_injector.inject(fault_type)

result = orchestrator.run_ooda_cycle()

t1 = time.time()

log_result({

'fault': fault_type,

'run': i,

'mttr_seconds': t1 - t0,

'diagnosis_correct': result.diagnosis == GROUND_TRUTH[fault_type],

'remediation_success': result.status == 'STEADY_STATE',

})

# 9. Week-by-Week Timeline

| Week | Focus | Bhuvanesh | Ritanya |
| --- | --- | --- | --- |
| 1 | Infra setup | Docker + Kafka running locally | GitHub repo + branch structure |
| 2 | Simulation | kafka_producer + Snowflake sink | patient_generator + fault_injector |
| 3 | Detection I | telemetry_collector + zscore | isolation_forest |
| 4 | Detection II | schema_entropy | ks_test + baseline tuning |
| 5 | Agent I | crisis_packet + prompts.py | LangChain tool wrappers (all 4) |
| 6 | Agent II | react_agent + orchestrator | End-to-end tests (3 fault types) |
| 7 | Hardening | memory_store (ChromaDB) | sql_sanitizer + validator |
| 8 | Evaluation | 120-test evaluation + charts | README + demo script + v1.0 tag |

# 10. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| OpenAI API costs exceed budget | Set max_tokens=500 per call. Use GPT-3.5-turbo in development, only GPT-4 for final evaluation. Budget ~$15 total. |
| LLM hallucinates a wrong fix | The ReAct loop forces the agent to query real tool outputs before acting. The SQL sanitizer blocks destructive commands. The validator rejects fixes that don't work. |
| Local Kafka Docker setup is unreliable | Pin Confluent Platform to 7.5.x in docker-compose.yml. Use confluent-kafka Python client (more stable than kafka-python). |
| Snowflake free trial expires | Use the 30-day trial only for Sprint 4 evaluation. Use a mock Snowflake client (MagicMock) in Sprints 1-3. |
| One team member falls behind | Each sprint's tasks are designed to be completable independently. The shared interface is the crisis_packet dict — once that's agreed in Week 5, both can work in parallel. |
| KS-Test produces too many false positives | Increase the baseline collection window to 2 hours. Add a 3-consecutive-alerts rule before raising a fault (reduces single-sample noise). |

# Appendix — Quick Reference

## A.1  Useful commands

# Start local infrastructure

docker-compose up -d

# Stream synthetic data

python simulator/kafka_producer.py --duration 30m

# Capture gold baseline

python simulator/gold_baseline.py --minutes 30

# Inject a fault

python simulator/fault_injector.py --fault schema

python simulator/fault_injector.py --fault data_quality

python simulator/fault_injector.py --fault performance

python simulator/fault_injector.py --fault security

python simulator/fault_injector.py --fault stall

# Run LARF (one OODA cycle)

python agent/orchestrator.py --once

# Run LARF (continuous mode)

python agent/orchestrator.py --continuous

# Run evaluation harness

pytest tests/test_end_to_end.py -v --tb=short

## A.2  Physiological ranges for data generator

| Vital sign | Normal range | Anomalous value to inject | Kafka field name |
| --- | --- | --- | --- |
| Heart rate | 60 – 100 BPM | > 200 or < 30 BPM | heart_rate |
| Systolic BP | 90 – 140 mmHg | > 200 or < 60 mmHg | bp_systolic |
| Diastolic BP | 60 – 90 mmHg | > 130 or < 40 mmHg | bp_diastolic |
| SpO2 | 95 – 100 % | < 80 % | spo2 |
| Temperature | 36.1 – 37.8 °C | > 42 or < 34 °C | temperature_c |